## Guidance & Instructions
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## Test Plan
TEST PLAN
Project Name: | Testing Notes Application – UI + API Hybrid Testing
Test Plan ID: | TP-001
Version: | To manually validate the Notes application functionality including UI operations, API operations, and UI/API synchronization.
Date: | 06-05-2026
Prepared By: | Adhithi
Approved By:
SCOPE
Features to be Tested:
User login functionality in UI
Note creation through UI
Display of newly created notes in UI
GET /notes API functionality
Validation of UI-created notes in API response
Note deletion using API
Validation of deleted notes removal from UI
Negative scenarios for UI and API validations
TESTING TYPE
Functional Testing
Regression Testing
Integration Testing
UAT
TEST ENVIRONMENT
Environment: | Dev / QA / Staging / Production
Browser/OS: | Chrome/Windows
TIMELINE
Start Date: | 2026-05-04
End Date: | 2026-05-07
RESOURCES
QA Lead: | Self(Adhithi)
QA Resources: | Individual Project
Test Data Provider:
RISKS & ASSUMPTIONS
Risks: | Notes may take some time to appear in the API after creating them in UI.
API may respond slowly sometimes during testing.
UI or API changes can affect test execution.
Assumptions: | The Notes application and APIs are working properly during testing.
Valid login credentials are available for testing.
Notes created or deleted are updated correctly in both UI and API.

## Test Scenarios
Section ID | Scenario Name | Description | Pre-conditions
TS-01 | Validate successful login | Verify that the user can login successfully using valid credentials | Valid user account should exist
TS-02 | Vadlidate note creation through UI | Verify that the user can create a new note by entering title and description | User should be logged into application
TS-03 | Validate instant note visibility | Verify that newly created note appears immediately in notes list without refresh | Note should be created successfully
TS-04 | Validate GET /notes API | Verify that GET /notes API returns all available notes successfully | API authentication should be successful
TS-05 | Validate UI and API data consistency | Verify that notes created through UI are correctly reflected in API response | Note should be created from UI
TS-06 | Validate note deletion using API | Verify that user can delete notes successfully using DELETE API | Existing note should be available
TS-07 | Validate deleted note removal from UI | Verify that deleted notes are removed from UI after API deletion | Note should be deleted through API
TS-08 | Validate negative scenarios | Verify application behavior for invalid inputs and invalid API requests | Application and API should be accessible

## Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-UI-01 | TS-01 | Verify login with valid credentials | Application should be launched | 1. Open Notes application | User should login successfully and Notes dashboard should be displayed | High | Not Executed
2. Enter valid email
3. Enter valid password
4. Click Login button
TC-UI-02 | TS-02 | Verify note creation from UI | User should be logged in | 1. Click Add Note button | New note should be created successfully and displayed in notes list | High | Not Executed
2. Enter note title
3. Enter note description
4. Click Save button
TC-UI-03 | TS-03 | Verify newly created note appears instantly | Note should be created successfully | 1. Create a new note | Newly created note should appear immediately without page refresh | High | Not Executed
2. Observe notes list after saving
TC-API-01 | TS-04 | Verify GET /notes API response | Valid API token should be generated | 1. Send GET /notes request | API should return status code 200 with notes list in response | High | Not Executed
2. Verify status code
3. Verify notes data in response
TC-E2E-01 | TS-05 | Verify UI created note matches API data | Note should be created from UI | 1. Create note through UI | UI note data should exactly match API response data | High | Not Executed
2. Call GET /notes API
3. Compare note details
TC-API-02 | TS-06 | Verify note deletion using API | Existing note should be available | 1. Send DELETE request using note ID | Deleted note should not be available in API response | High | Not Executed
2. Verify response status code
TC-E2E-02 | TS-07 | Verify deleted note disappears from UI | Note should be deleted using API | 1. Refresh Notes page | Deleted note should not appear in UI | High | Not Executed
2. Verify deleted note is not displayed
TC-NEG-01 | TS-08 | Verify invalid login and invalid API requests | Application should be accessible | 1. Enter invalid email and password | Application should display proper error messages and API should return proper status codes | Medium | Not Executed
2. Click Login button

## Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Email: example@test.com | Valid login validation
Password: Test@123
TD-002 | Invalid User | Email: invalid@test.com | Negative login validation
Password: Wrong@123
TD-003 | Note Data | Title: Automation Note | Note creation validation
Description: Notes app testing
TD-004 | API Token | Bearer Token for Notes API authentication | API testing and authorization
TD-005 | Delete Note Data | Note ID for delete operation | Note deletion validation

## Test Execution
Test Case ID | Cycle | Test Case Title | Pass/Fail | Remark
TC-UI-01 | Cycle-1 | Verify login with valid credentials | Pass | Login successful and dashboard displayed
TC-UI-02 | Cycle-1 | Verify note creation from UI | Pass | Note created successfully
TC-UI-03 | Cycle-1 | Verify newly created note appears instantly | Pass | Note displayed immediately without refresh
TC-API-01 | Cycle-1 | Verify GET /notes API response | Pass | API returned notes list successfully
TC-E2E-01 | Cycle-1 | Verify UI created note matches API data | Pass | UI and API note details matched
TC-API-02 | Cycle-1 | Verify note deletion using API | Pass | Note deleted successfully using API
TC-E2E-02 | Cycle-1 | Verify deleted note disappears from UI | Pass | Deleted note removed from UI successfully
TC-NEG-01 | Cycle-1 | Verify invalid login validation | Fail | Proper validation message not displayed

## Traceability Matrix
Requirement ID | Test Case ID | Requirements Description | Test Coverage | Status
FR-01 | TC-UI-01 | UI login should work with valid credentials | Manual UI Login Testing | Covered
FR-02 | TC-UI-02 | Create note via UI | Manual Create Note Testing | Covered
FR-03 | TC-UI-03 | Note should appear instantly in UI list after creation | Manual UI Validation | Covered
FR-04 | TC-API-01 | API GET /notes should return notes list successfully | Manual API Testing using Postman | Covered
FR-05 | TC-E2E-01 | UI-created note must appear in API response | End-to-End Validation (UI + API) | Covered
FR-06 | TC-API-02 | Delete note successfully via API | Manual Delete API Testing | Covered
FR-07 | TC-E2E-02 | Deleted note must disappear from UI | End-to-End Deletion Validation | Covered
FR-08 | TC-PERF-01 | API response time should be less than 2 seconds | Manual Performance Validation | Covered
FR-09 | TC-NEG-01 | Negative scenarios for UI and API should be handled properly | Negative Testing (UI & API)

## Defect Report
PROJECT INFORMATION
Project Name: | Notes Application Automation Testing
Test Cycle:
Report Date:
Prepared By: | Adhithi Karrolla
EXECUTION SUMMARY
Total Test Cases: | 17
Test Cases Executed: | 17
Test Cases Passed: | 17
Test Cases Failed: | 0
Pass Percentage:
DEFECT SUMMARY
Total Defects: | 0
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 0
Low Defects: | 0
Open Defects: | 0
Closed Defects: | 0
CONCLUSION
Testing Status: | In Progress
Release Readiness:
Overall Recommendation: | Not Ready for Production
REMARKS